## Cost Estimate & Budget
In2Fitness Project Cost Estimate
Prepared by:WangYiZhuo | Date: | 30/07/2024
Note: Change the WBS items and other entries to meet your project needs. This data is from Figure 7-1 of Schwalbe's text | [5 empty] | SAMPLE
Information Technology Project Management, Fourth Edition. Also make sure the formulas work properly based on the data you enter.
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total | Staffing
WBS Items | [5 empty] | PM
1. Project Management |  |  |  | 250560 | 52.21% | System Analyst
1.1 Project manager | 960 | 105 | 100800 |  |  | Developer ( Programmer & Web designer & App Developer)
1.2 Project team members | 1920 | 78 | 149760 |  |  | Tester
System Designer
2. Hardware |  |  |  | 77400 | 16.13%
2.1 Handheld devices | 100 | 610 | 61000
2.2 Servers | 4 | 4100 | 16400 |  |  | Duration
3. Software |  |  |  | 21000 | 4.375% | Months | Weeks | Weeks per week |  | Total days | Work hours per day | Hours
3.1 Licensed software | 100 | 210 | 21000 |  |  | 3 | 4 | 5 |  | 60 | 7 | 420
4. Training and Support |  |  |  | 51000 | 10.63% | Staffing
4.1 Trainee cost | 100 | 510 | 51000 |  |  |  | Pay Rate | Total Hours Needed | Total Pay
[6 empty] | PM | 100 | 200 | 20000
[6 empty] | SA | 85 | 30 | 2550
5. Reserves (20% of total estimate) |  |  | 79992 | 79992 | 16.67% | Developer | 75 | 100 | 7500
Total project cost estimate |  |  |  | 479952 |  | Tester | 65 | 20 | 1300
[6 empty] | SD | 47 | 20 | 940
[8 empty] | Total | 32290
Hardware
Server
Devices
Software
Licenced Software