## WBS Template
Work Breakdown Structure Template for Project Name
Prepared by:WangYiZhuo |  |  |  | Date: | 2024.7.29
| Duration | Predecessor | Finish | Predecessore
Project Tracking Database | 80.5 days | Mon 3/01/2024 | Mon 25/04/2024
Initiating Tasks | 9 days | Mon 3/01/2024 | Thu 13/01/2024
Initial Meeting with Project Sponsor | 1 day | Mon 3/01/2024 | Mon 3/01/2024
Research on Similar Projects | 3 days | Tue 4/01/2024 | Thu 6/01/2024
Drafting Project Requirements | 3 days | Fri 7/01/2024 | Tue 11/01/2024
Review with Sponsor and Stakeholders | 1 day | Wed 12/01/2024 | Wed 12/01/2024
Developing the Project Charter | 1 day | Thu 13/01/2024 | Thu 13/01/2024
Charter Approval and Signing | 0 days | Thu 13/01/2024 | Thu 13/01/2024
Planning tasks | 10 days | Fri 14/01/2024 | Thu 27/01/2024
Develop Work Breakdown Structure | 5 days | Fri 14/01/2024 | Thu 20/01/2024
Estimate Durations | 2 days | Fri 21/01/2024 | Mon 24/01/2024
Assign Resources | 4 days | Fri 21/01/2024 | Wed 26/01/2024
Determine Task Relationships | 2 days | Fri 21/01/2024 | Mon 24/01/2024
Enter Cost Information | 3 days | Fri 21/01/2024 | Tue 25/01/2024
Review Gantt and PERT Chart Information | 1 day | Tue 25/01/2024 | Tue 25/01/2024
Review Plan with Stakeholders | 1 day | Thu 27/01/2024 | Thu 27/01/2024
Plans Approved | 0 days | Thu 27/01/2024 | Thu 27/01/2024
Executing tasks | 55.5 days | Fri 28/01/2024 | Fri 15/04/2024
Gather information | 10 days | Fri 28/01/2024 | Thu 10/02/2024
Investigate relevant websites | 3 days | Fri 28/01/2024 | Tue 1/02/2024
Compiled comprehensive information on design and web hosting | 2.5 days | Fri 11/02/2024 | Tue 15/02/2024
Create a template for web pages | 1 day | Tue 15/02/2024 | Wed 16/02/2024
Design a site map or hierarchy chart | 1 day | Tue 15/02/2024 | Wed 16/02/2024
Convert photographs and other information to digital format | 5 days | Tue 15/02/2024 | Tue 22/02/2024
Develop web pages | 10 days | Tue 22/02/2024 | Tue 8/03/2024
Evaluate the pages and the website | 3 days | Tue 8/03/2024 | Fri 11/03/2024
Deploy the site on the customer's web server | 5 days | Fri 11/03/2024 | Fri 18/03/2024
Site ready for review. | 0 days | Fri 18/03/2024 | Fri 18/03/2024
Obtain customer feedback | 5 days | Fri 18/03/2024 | Fri 25/03/2024
Integrate changes | 5 days | Fri 25/03/2024 | Fri 1/04/2024
Develop training materials for updating pages | 5 days | Fri 1/04/2024 | Fri 8/04/2024
Provide training to the customer on how to update web pages | 5 days | Fri 8/04/2024 | Fri 15/04/2024
Training finished | 0 days | Fri 15/04/2024 | Fri 15/04/2024
Controlling tasks | 68.13 days | Fri 14/01/2024 | Wed 20/04/2024
Status report | 68.13 days | Fri 14/01/2024 | Wed 20/04/2024
Status report 1 | 1 hr | Fri 14/01/2024 | Fri 14/01/2024
Status report 2 | 1 hr | Fri 14/01/2024 | Fri 14/01/2024
Status report 3 | 1 hr | Wed 19/01/2024 | Wed 19/01/2024
Status report 4 | 1 hr | Wed 26/01/2024 | Wed 26/01/2024
Status report 5 | 1 hr | Wed 2/02/2024 | Wed 2/02/2024
Status report 6 | 1 hr | Wed 9/02/2024 | Wed 9/02/2024
Status report 7 | 1 hr | Wed 16/02/2024 | Wed 16/02/2024
Status report 8 | 1 hr | Wed 23/02/2024 | Wed 23/02/2024
Status report 9 | 1 hr | Wed 2/03/2024 | Wed 2/03/2024
Status report 10 | 1 hr | Wed 9/03/2024 | Wed 9/03/2024
Status report 11 | 1 hr | Wed 16/03/2024 | Wed 16/03/2024
Status report 12 | 1 hr | Wed 23/03/2024 | Wed 23/03/2024
Status report 13 | 1 hr | Wed 30/03/2024 | Wed 30/03/2024
Status report 14 | 1 hr | Wed 6/04/2024 | Wed 6/04/2024
Status report 15 | 1 hr | Wed 13/04/2024 | Wed 13/04/2024
Status report 16 | 1 hr | Wed 20/04/2024 | Wed 20/04/2024
Closing tasks | 6 days | Fri 15/04/2024 | Mon 25/04/2024
Prepare final project report | 3 days | Fri 15/04/2024 | Wed 20/04/2024
Present final project to stakeholders | 1 day | Wed 20/04/2024 | Thu 21/04/2024
Prepare lessons learned | 2 days | Thu 21/04/2024 | Mon 25/04/2024

## Sample WBS
SAMPLE
| Task Name | Duration | Start | Finish | Predecessors | WBS
| Project Tracking Database | 80.5 days | Mon 3/01/11 | Mon 25/04/11 |  |  |  | Initiation | Duration | Predessors
| Initiating tasks | 9 days | Mon 3/01/11 | Thu 13/01/11 |  |  |  |  | h d w
| Initial meeting with project sponsor | 1 day | Mon 3/01/11 | Mon 3/01/11 |  |  | 1 | Kickoff Meeting | 2h
| Research similar projects | 3 days | Tue 4/01/11 | Thu 6/01/11 | 2 |  | 1.1 | Develop Business Case
| Draft project requirements | 3 days | Fri 7/01/11 | Tue 11/01/11 | 3 |  | 1.2 | Develop Business Charter
| Review with sponsor and other stakeholders | 1 day | Wed 12/01/11 | Wed 12/01/11 | 4 |  | 1.3 | Charter signed
| Develop project charter | 1 day | Thu 13/01/11 | Thu 13/01/11 | 5
| Charter signed | 0 days | Thu 13/01/11 | Thu 13/01/11 | 6
| Planning tasks | 10 days | Fri 14/01/11 | Thu 27/01/11 | 7 |  | 2 | Planning
| Develop WBS | 5 days | Fri 14/01/11 | Thu 20/01/11 | 7 |  | 2.1 | Develop WBS
| Estimate durations | 2 days | Fri 21/01/11 | Mon 24/01/11 | 9 |  |  | Develop Gantt Chart
| Assign resources | 4 days | Fri 21/01/11 | Wed 26/01/11 | 9 |  |  | Create Cost Benefit Analysis
| Determine task relationships | 2 days | Fri 21/01/11 | Mon 24/01/11 | 9 |  |  | Create Cost Estimation
| Enter cost information | 3 days | Fri 21/01/11 | Tue 25/01/11 | 9 |  |  | Approve WBS & Budget
| Review Gantt and PERT chart information | 1 day | Tue 25/01/11 | Tue 25/01/11 | 12 |  |  | Develop Risk Register
| Review plan with stakeholders | 1 day | Thu 27/01/11 | Thu 27/01/11 | 10,11,12,14 |  |  | Develop Stakeholder Management Strategy
| Plans approved | 0 days | Thu 27/01/11 | Thu 27/01/11 | 15 |  |  | Planned Approved | 0
| Executing tasks | 55.5 days | Fri 28/01/11 | Fri 15/04/11 | 15
| Collect information | 10 days | Fri 28/01/11 | Thu 10/02/11 | 16 |  | 3 | Execution
| Research related web sites | 3 days | Fri 28/01/11 | Tue 1/02/11 | 15 |  |  | Create Team Contract
| Collected detailed info on design and web space | 2.5 days | Fri 11/02/11 | Tue 15/02/11 | 18,19 |  |  | Create training and Support Plan
| Develop template for web pages | 1 day | Tue 15/02/11 | Wed 16/02/11 | 20 |  |  | Analysis
| Create site map/hierarchy chart | 1 day | Tue 15/02/11 | Wed 16/02/11 | 20 |  |  | Design ????
| Digitize photographs and other info | 5 days | Tue 15/02/11 | Tue 22/02/11 | 20 |  |  | Develop System
| Create web pages | 10 days | Tue 22/02/11 | Tue 8/03/11 | 21,22,23 |  |  | Develop Mobile App
| Test pages and the site | 3 days | Tue 8/03/11 | Fri 11/03/11 | 24 |  | 18 | Testing & Debug
| Implement site on customer's web server | 5 days | Fri 11/03/11 | Fri 18/03/11 | 25 |  |  | Implement System |  | 18
| Site available for review | 0 days | Fri 18/03/11 | Fri 18/03/11 | 26 |  |  | Implement App |  | 18
| Get customer feedback | 5 days | Fri 18/03/11 | Fri 25/03/11 | 27 |  |  | Training |  | 18
| Incorporate changes | 5 days | Fri 25/03/11 | Fri 1/04/11 | 28 |  |  | System Implemented | 0
| Create training materials on updating pages | 5 days | Fri 1/04/11 | Fri 8/04/11 | 29
| Train customer on updating web pages | 5 days | Fri 8/04/11 | Fri 15/04/11 | 30
| Training completed | 0 days | Fri 15/04/11 | Fri 15/04/11 | 31 |  | 4 | Monitoring and Controlling
| Controlling tasks | 68.13 days | Fri 14/01/11 | Wed 20/04/11 | 7 |  |  | Status Report
| Status report | 68.13 days | Fri 14/01/11 | Wed 20/04/11 |  |  |  | Performance Report
| Status report 1 | 1 hr | Fri 14/01/11 | Fri 14/01/11
| Status report 2 | 1 hr | Fri 14/01/11 | Fri 14/01/11 |  |  | 5 | Closing
| Status report 3 | 1 hr | Wed 19/01/11 | Wed 19/01/11 |  |  |  | Prepare Final Project report
| Status report 4 | 1 hr | Wed 26/01/11 | Wed 26/01/11 |  |  |  | Present Project
| Status report 5 | 1 hr | Wed 2/02/11 | Wed 2/02/11 |  |  |  | Lesson learned report
| Status report 6 | 1 hr | Wed 9/02/11 | Wed 9/02/11 |  |  |  | Sign Client Acceptance form
| Status report 7 | 1 hr | Wed 16/02/11 | Wed 16/02/11 |  |  |  | Project Completed
| Status report 8 | 1 hr | Wed 23/02/11 | Wed 23/02/11
| Status report 9 | 1 hr | Wed 2/03/11 | Wed 2/03/11
| Status report 10 | 1 hr | Wed 9/03/11 | Wed 9/03/11
| Status report 11 | 1 hr | Wed 16/03/11 | Wed 16/03/11
| Status report 12 | 1 hr | Wed 23/03/11 | Wed 23/03/11
| Status report 13 | 1 hr | Wed 30/03/11 | Wed 30/03/11
| Status report 14 | 1 hr | Wed 6/04/11 | Wed 6/04/11
| Status report 15 | 1 hr | Wed 13/04/11 | Wed 13/04/11
| Status report 16 | 1 hr | Wed 20/04/11 | Wed 20/04/11
| Closing tasks | 6 days | Fri 15/04/11 | Mon 25/04/11 | 17
| Prepare final project report | 3 days | Fri 15/04/11 | Wed 20/04/11 | 30
| Present final project to stakeholders | 1 day | Wed 20/04/11 | Thu 21/04/11 | 52
| Prepare lessons learned | 2 days | Thu 21/04/11 | Mon 25/04/11 | 53